## Sprint 1
Sprint 1 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 1 (05/59 - 10/9) | #REF!
Document | 7
Introduction | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Concept Diagram | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Entity Relationship Diagram | 3 | Thanhth | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0 | 0
Usecase Overview |  | Huanpm | Complete |  | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Mock UI | 0
Login UI |  | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Sign up UI |  | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Tour Match screen Android |  | Huanpm | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0
View Match |  | thanhth | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0
Football field sceen Android |  | Thanhth | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 3
Sprint 3 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 3 (18/9 - 24/9) | #REF!
Design User Interface for Mobile Application | 7
Profile | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Deposit | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Detail Bill | 3 | Thanhth | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0 | 0
Notify UI |  | Huanpm | Complete |  | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Design User Interface for Web Application | 0
Set price |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Set time enable |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Promotion |  | Huanpm | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0
Notify UI |  | thanhth | Complete | 6 | Day 1: 6; Day 2: 4; Day 3: 2; Day 4: 0
Field |  | Thanhth | Complete | 8 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0
WebService Architecture |  | Hieupt | Complete | 8 | Day 1: 8; Day 2: 7; Day 3: 5; Day 4: 0
Physical Database Diagram |  | Hieupt | Complete | 8 | Day 1: 8; Day 2: 6; Day 3: 6; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 4
Sprint 4 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 4 (25/9 - 1/10) | #REF!
User Sign In | 4
Login API | 2 | Hieupt | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 0; Day 4: 0 | 0
Call Login API | 2 | Hieupt | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0 | 0
User Sign Up | 2
Sign up API |  | Thanhth | Complete | 4 | Day 1: 4; Day 2: 0; Day 3: 0; Day 4: 0
Call Sign Up API |  | Thanhth | Complete | 4 | Day 1: 4; Day 2: 2; Day 3: 2; Day 4: 0
Field Owner Sign In | 0
Login API | 2 | Quymm | Complete | 4 | Day 1: 4; Day 2: 4; Day 3: 4; Day 4: 0 | 0
Call Login API | 2 | Quymm | Complete | 4 | Day 1: 2; Day 2: 2; Day 3: 0; Day 4: 0 | 0
Field Owner Sign Up | 0
Sign up API |  | HuanPM | Complete | 4 | Day 1: 4; Day 2: 0; Day 3: 0; Day 4: 0
Call Sign Up API |  | HuanPM | Complete | 4 | Day 1: 4; Day 2: 0; Day 3: 0; Day 4: 0
Create Field | 0
Create Field API |  | Quymm | Complete | 8 | Day 1: 4; Day 2: 0; Day 3: 0; Day 4: 0
Call Create Field API |  | Quymm | Complete | 8 | Day 1: 8; Day 2: 8; Day 3: 4; Day 4: 0
Create Time Enable | 0
Create Time Enable API |  | Thanhth | Complete | 12 | Day 1: 12; Day 2: 8; Day 3: 4; Day 4: 0
Call Create Time Enable API |  | Thanhth | Complete | 12 | Day 1: 12; Day 2: 12; Day 3: 6; Day 4: 0
Reserve Friendly Match | 0
Create Reserve Friendly Match API |  | Hieupt | Complete | 12 | Day 1: 8; Day 2: 4; Day 3: 0; Day 4: 0
Call Reserve Friendly Match API |  | Hieupt | Complete | 12 | Day 1: 12; Day 2: 12; Day 3: 6; Day 4: 0
Search Field | 0
Create Search Field API |  | HuanPM | Complete | 6 | Day 1: 6; Day 2: 0; Day 3: 0; Day 4: 0
Call Search Field API |  | HuanPM | Complete | 6 | Day 1: 6; Day 2: 6; Day 3: 0; Day 4: 0
Get Match By Day | 0
Create Get match bu day API |  | Hieupt | Complete | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0
Call get match by day API |  | Hieupt | Complete | 6 | Day 1: 6; Day 2: 0; Day 3: 0; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 5
Sprint 5 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 5 (2/10 - 8/5) | #REF!
Create Matching Request | 4
Create create matching request API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Call create matching request API | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Mapping Matching Requestes | 2
Create mapping maching requests API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call mapping maching request API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Checkout | 0
Conect paypal API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Deposit to system | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 6
Sprint 6 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 6 (09/10 - 15/10) | #REF!
Set favorite Field | 4
Create Set Favorite Field API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Call Set field API | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Get Field top nearest | 2
Create get field top nearest API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call get field top nearest API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Edit Profile | 0
Create edit profile API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Call edit profile API | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Set Black List | 0
Create set black list API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call set black list API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 7
Sprint 7 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 7 (16/10 - 22/10) | #REF!
Mapping Matching Requestes | 2
Mapping Matching Requestes with point | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Report field owner | 2
Create report filed owner API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call report field owner API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Report player | 0
Create report player API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Call create report player API | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Rating field Owner | 0
Create rating filed owner API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call rating field owner API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Rating player | 0
Create rating player API |  | Thanhth | Complete | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0
Call create rating player API |  | Thanhth | Complete | 6 | Day 1: 6; Day 2: 0; Day 3: 0; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 8
Sprint 8 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 8 (23/10 - 29/10) | #REF!
Mapping Matching Requestes | 2
Mapping Matching Requestes with position | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Deposit | 2
Deposit with paypal |  | HuanPM | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Deposit with ngan luong |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Voucher | 0
Create create voucher API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Apply voucher to bill |  | Thanhth | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 0; Day 4: 0
Call create voucher API | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Promotion | 0
Create promotion API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call create promotion API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## sprint 9
Sprint 9 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 9 (30/10 - 05/11) | #REF!
Mapping Matching Requestes | 2
Mapping Matching Requestes with best field | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Affective Time Enable | 2
Time enable with peak time and low time |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Standard Price | 0
Create standard price API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Call create standard price API | 2 | Quymm | Complete | 3 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0 | 0
Notification | 0
Noty to user |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Noty to field owner |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!

## Sprint 10
Sprint 10 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Sprint 10 (06/11 - 12/11) | #REF!
Block user | 2
Create block user API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call block user API | 2 | Hieupt | Complete | 2 | Day 1: 2; Day 2: 0; Day 3: 0; Day 4: 0 | 0
Block field owner | 0
Create block field owner API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Call block field owner API |  | Quymm | Complete | 4 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 0
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!