## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Assigned to Sprint
Sprint 1 | Yes | Yes | High | Complete | Yes
Introduction | Yes | Yes | High | Complete | Yes
Concept Diagram | Yes | Yes | Medium | Complete | Yes
Entity Relationship Diagram | Yes | Yes | High | Complete | Yes
Usecase Overview | Yes | Yes | Medium | Complete | Yes
Mock UI | Yes | Yes | Medium | Complete | Yes
Sprint 2 | Yes | Yes | Medium | Complete | Yes
Study ReactJs | Yes | Yes | High | Complete | Yes
Study Android | Yes | Yes | High | Complete | Yes
Study Spring Framework | Yes | Yes | High | Complete | Yes
Sprint 3 | Yes | Yes | Medium | Complete | Yes
Design User Interface for Mobile Application | Yes | Yes | Medium | Complete | Yes
Design User Interface for Web Application | Yes | Yes | Medium | Complete | Yes
Physical Database Diagram | Yes | Yes | High | Complete | Yes
WebService Architecture | Yes | Yes | High | Complete | Yes
Sprint 4 | Yes | Yes | Medium | Complete | Yes
User Sign In | Yes | Yes | Medium | Complete | Yes
User Sign Up | Yes | Yes | Medium | Complete | Yes
Field Owner Sign In | Yes | Yes | Medium | Complete | Yes
Field Owner Sign Up | Yes | Yes | Medium | Complete | Yes
Create Field | Yes | Yes | Low | Complete | Yes
Create Time Enable | Yes | Yes | Medium | Complete | Yes
Reserve Friendly Match | Yes | Yes | Medium | Complete | Yes
Search Field
Get Match By Day | Yes | Yes | Medium | Complete | Yes
Sprint 5 | Yes | Yes | Medium | Complete | Yes
Create Matching Request | Yes | Yes | Medium | Complete | Yes
Mapping Matching Requestes | Yes | Yes | Medium | Complete | Yes
Checkout | Yes | Yes | Medium | Complete | Yes
Sprint 6 | Yes | Yes | Medium | Complete | Yes
Set favorite Field | Yes | Yes | Low | Complete | Yes
Get Field top nearest | Yes | Yes | High | Complete | Yes
Edit Profile | Yes | Yes | Medium | Complete | Yes
Set Black List | Yes | Yes | Low | Complete | Yes
Sprint 7 | Yes | Yes | Medium | Complete | Yes
Mapping Matching Requestes | Yes | Yes | High | Complete | Yes
Report field owner | Yes | Yes | Low | Complete | Yes
Report player | Yes | Yes | Low | Complete | Yes
Rating field Owner | Yes | Yes | Low | Complete | Yes
Rating player | Yes | Yes | Low | Complete | Yes
Sprint 8 | Yes | Yes | Medium | Complete | Yes
Mapping Matching Requestes | Yes | Yes | Medium | Complete | Yes
Deposit | Yes | Yes | Medium | Complete | Yes
Voucher | Yes | Yes | Low | Complete | Yes
Promotion | Yes | Yes | Medium | Complete | Yes
Sprint 9 | Yes | Yes | Medium | Complete | Yes
Mapping Matching Requestes | Yes | Yes | Medium | Complete | Yes
Affective Time Enable | Yes | Yes | Medium | Complete | Yes
Standard Price | Yes | Yes | Medium | Complete | Yes
Notification | Yes | Yes | Medium | Complete | Yes
Sprint 10 | Yes | Yes | Medium | Complete | Yes
Block user | Yes | Yes | Medium | Complete | Yes
Block field owner | Yes | Yes | Medium | Complete | Yes
Sprint 11 | Yes | Yes | Medium | Complete | Yes
Test Plan | Yes | Yes | Medium | Complete | Yes
Quality Assurance | Yes | Yes | Medium | Complete | Yes
Sprint 12 | Yes | Yes | Medium | Complete | Yes
Installation guide | Yes | Yes | Medium | Complete | Yes
User guide | Yes | Yes | Medium | Complete | Yes