## Sprint 1
Sprint 1 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 1 (08/5 - 15/5) | 19
Document | 14
Introduction | 2 | LamTT | Complete | 16 | 16 | 12 | 8 | 6 | 4 | 2 | 0
Concept Diagram | 2 | HieuLN | Complete | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
Class Diagram | 2 | HieuLN | Complete | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0
Entity Relationship Diagram | 2 | HieuLN | Complete | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0
Usecase Overview | 3 | HieuLN | Complete | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
Mock UI | 3 | QuangNN | Complete | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0
Study | 5
Research WebRTC | 5 | NguyenDH | Complete | 30 | 30 | 25 | 20 | 16 | 10 | 5 | 0
Total |  |  |  | 90 | 90 | 74 | 56 | 44 | 27 | 11 | 0

## Sprint 2
Sprint 2 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 2 (15/5 - 22/5) | 8
Study | 8
React Native | 4 | HieuLN NguyenDH QuangNN LamTT | Complete | 30 | 30 | 30 | 30 | 20 | 10 | 0 | 0
Play Framework | 4 | HieuLN NguyenDH QuangNN LamTT | Complete | 30 | 20 | 10 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 60 | 50 | 40 | 30 | 20 | 10 | 0 | 0

## Sprint 3
Sprint 3 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 3 (22/5 - 29/5) | 25
Login | 3
Login UI | 2 | QuangNN | Complete | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
Signup UI | 1 | QuangNN | Complete | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
Teacher Signup | 4
About You UI | 1 | HieuLN | Complete | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0
Choose Experience | 1 | HieuLN | Complete | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Set Avaiability | 1 | HieuLN | Complete | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Intro Video | 1 | HieuLN | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Create Course | 5
Course Intro UI | 1 | QuangNN | Complete | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Create Chapter, Lesson UI | 3 | QuangNN | In Progress | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 2
SetPrice UI | 1 | QuangNN | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
DashBoard | 6
Upcoming UI | 1 | NguyenDH | Complete | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
DashBoard UI | 2 | NguyenDH | Complete | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0
Search | 3 | NguyenDH | In Progress | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2
Document | 7
Physical Database Diagram | 2 | HieuLN | Complete | 3 | 5 | 3 | 2 | 0 | 0 | 0 | 0
Mobile Architecture | 2 | HieuLN | Complete | 2 | 3 | 3 | 3 | 3 | 0 | 0 | 0
WebService Architecture | 3 | HieuLN | Complete | 2 | 3 | 3 | 3 | 3 | 3 | 0 | 0
Total |  |  |  | 58 | 60 | 52 | 47 | 32 | 19 | 8 | 4

## Sprint 4
Sprint 4 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 4 (29/5 - 4/6) | 29
Login | 5
API Login | 2 | HieuLN | Complete | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0
Mobile Login | 2 | NguyenDH | Complete | 8 | Day 1: 8; Day 2: 2; Day 3: 0
API Signup | 1 | LamTT | Complete | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0
Mobie Signup | 1 | LamTT | Complete | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0
Teacher Signup | 6
Backend Save file to server | 1 | HieuLN | Complete | 4 | Day 1: 4; Day 2: 6; Day 3: 0
API Teacher Signup | 2 | NguyenDH | Complete | 18 | 18 | 10 | 10 | 10 | 10 | 8 | 0
Mobile Teacher Signup | 3 | NguyenDH | Complete | 12 | 12 | 12 | 12 | 12 | 8 | 2 | 0
Create Course | 4
Course Intro UI | 1 | QuangNN | Complete | 6 | 6 | 2 | 2 | 2 | 0 | 2 | 0
Create Chapter, Lesson UI | 3 | QuangNN | Complete | 10 | 10 | 8 | 8 | 6 | 6 | 6 | 6
DashBoard | 5
UI home screen | 1 | QuangNN | Complete | 4 | 4 | 4 | 4 | 0 |  | 0
DashBoard UI | 2 | QuangNN | Complete | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 6
API Search | 2 | NguyenDH | Pending | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8
Mobile Search | 2 | NguyenDH | Pending | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Get Learner Profile | 8 | LamTT | In progess | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4
Document | 2
Class Diagram | 2 | HieuLN, LamTT | Complete | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0
Study | 7
Shiro security | 2 | HieuLN | Complete | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0
Json web token | 2 | HieuLN | Complete | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 0
Call API React Native | 3 | NguyenDH | Complete | 12 | 12 | 8 | 2 | 0 | 0 | 0 | 0
Total |  |  |  | 100 | 100 | 76 | 73 | 58 | 46 | 40 | 28

## Sprint 5
Sprint 5 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 5 (5/6 - 12/6) | 53
Login | 4
Login FB, Google OAuth2 | 4 | HieuLN | Complete | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0
Create Course | 27
Create course | 5 | QuangNN | Complete | 10 | 10 | 8 | 5 | 0 | 0 | 0 | 0
Create Chapter | 4 | QuangNN | Complete | 8 | 8 | 8 | 8 | 4 | 2 | 0 | 0
Create Lesson | 4 | HieuLN | Complete | 8 | 8 | 8 | 8 | 4 | 4 | 2 | 2
View Course info | 2 | QuangNN | Complete | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2
Edit Course | 3 | QuangNN | Complete | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0
Edit Chapter | 3 | QuangNN | Complete | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0
Edit Lesson | 3 | HieuLN | Complete | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0
Remove Lesson | 3 | HieuLN | Complete | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
DashBoard | 8
Search Course | 4 | NguyenDH | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Search Teacher | 4 | NguyenDH | Pending | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Schedule | 12
Set Available Timeslot | 6 | NguyenDH | Complete | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
View Available Timeslot | 6 | NguyenDH | Complete | 15 | 15 | 8 | 2 | 0 | 0 | 0 | 0
Profile | 2
View Teacher Profile | 2 | LamTT | Complete | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
Algorithm | 0
Collaborative Filtering |  | LamTT | Complete | 40 | 40 | 32 | 24 | 16 | 8 | 4 | 0
Total |  |  |  | 159 | 159 | 140 | 119 | 89 | 64 | 40 | 22

## Sprint 6
Sprint 6 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 6 (12/6 - 19/6) | 42
Learner Request | 16
Section Detail | 4 | QuangNN | Complete | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
View list requestUI | 4 | QuangNN | Complete | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0
Send request | 4 | HieuLN | Complete | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
Request detail | 4 | QuangNN | Complete | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0
Check request | 6 | HieuLN | Complete | 16 | 16 | 10 | 10 | 10 | 5 | 0 | 0
Profile | 6
Learner profile | 3 | LamTT | Complete | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0
Edit profile | 3 | LamTT | Pending | 8 | 8 | 6 | 6 | 3 | 0 | 0 | 0
Dashboard | 3
Upcoming section | 3 | QuangNN | Complete | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
Schedule | 6
Edit free time slot | 3 | NguyenDH | Pending | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Remove free time slot | 3 | NguyenDH | Pending | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Search | 17
Suggestion | 5 | NguyenDH | Complete | 15 | 15 | 10 | 8 | 4 | 4 | 4 | 0
Search course | 6 | NguyenDH | Complete | 10 | 10 | 8 | 4 | 0 | 0 | 0 | 0
Filter | 6 | NguyenDH | Complete | 10 | 10 | 10 | 8 | 8 | 6 | 4 | 0
Total |  |  |  | 123 | 123 | 100 | 77 | 53 | 35 | 24 | 16

## Sprint 7
Sprint 7 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 7 (26/6 - 03/7) | 24
Profile | 6
Teacher Profile | 3 | QuangNN | Complete | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
List Rating | 3 | QuangNN | Complete | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
API Profile | 4 | HieuLN | Complete | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
Video Call | 7
Demo video call | 7 | NguyenDH | Complete | 40 | 40 | 35 | 25 | 17 | 12 | 6 | 0
Setting | 11
Update profile | 5 | LamTT | Complete | 15 | 15 | 10 | 6 | 4 | 0 | 0 | 0
Update language | 6 | LamTT | Complete | 10 | 10 | 10 | 10 | 10 | 6 | 4 | 0
Setting UI | 3 | QuangNN | Complete | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
Change Password | 3 | QuangNN | Complete | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0
Logout | 3 | QuangNN | Complete | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
Total |  |  |  | 64 | 64 | 51 | 29 | 17 |  |  | 0

## Sprint 8
Sprint 8 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 8 (3/7 - 10/7) | 33
Video call | 6
Implement video call | 6 | NguyenDH | Complete | 30 | 30 | 25 | 18 | 10 | 5 | 0 | 0
Receive call service | 5 | NguyenDH | Complete | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
Receive call screen | 3 | QuangNN | Complete | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
Dashboard | 3
Learning session | 3 | QuangNN | Complete | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
API Session | 4 | HieuLN | Complete | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
Setting | 12
Change Timezone | 4 | LamTT | Complete | 10 | 10 | 8 | 6 | 4 | 4 | 4 | 0
Change Language | 4 | LamTT | Complete | 10 | 10 | 8 | 8 | 4 | 2 | 2 | 2
Change Currency | 4 | LamTT | Complete | 10 | 10 | 8 | 8 | 8 | 4 | 2 | 0
Change Country | 4 | LamTT | Complete | 8 | 8 | 6 | 6 | 6 | 6 | 3 | 0
Request | 12
Sending Request | 4 | QuangNN | Complete | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
Incoming Request | 4 | QuangNN | Complete | 10 | 10 | 10 | 6 | 0 | 0 | 0 | 0
Cancel Request | 4 | QuangNN | Complete | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0
API Request | 6 | HieuLN | Complete | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
Total |  |  |  | 128 | 128 | 105 | 84 | 52 | 34 | 16 | 2

## Sprint 9
Sprint 9 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 9 (10/7 - 17/7) | 15
Video call | 3
Turn on/off camera, sound | 3 | NguyenDH | Pending | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Switch camera | 2 | NguyenDH | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
End Call | 3 | NguyenDH | Complete | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
Chat while calling | 6 | QuangNN | Complete | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
Setting | 8
Refactor load currency | 4 | LamTT | Complete | 10 | 10 | 10 | 5 | 5 | 0 | 0 | 0
Refactor load timezone | 4 | LamTT | Pending | 10 | 10 | 10 | 10 | 6 | 2 | 0 | 0
Dictionary | 6
Translate | 3 | LamTT | Complete | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0
Set languages | 3 | HieuLN | Complete | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0
Swap languages | 2 | HieuLN | Complete | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
Dictionary UI | 3 | QuangNN | Complete | 10 | 10 | 10 | 10 | 6 | 4 | 2 | 0
Notification | 6
Research Push notification | 6 | NguyenDH | Complete | 40 | 40 | 32 | 25 | 16 | 8 | 0 | 0
Request notification | 4 | NguyenDH | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Message | 4
Load chat message | 4 | NguyenDH | Complete | 40 | 40 | 32 | 25 | 16 | 8 | 0 | 0
Total |  |  |  | 151 | 151 | 139 | 119 | 90 | 61 | 41 | 35

## Sprint 10
Sprint 10 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 10 (17/7 - 24/7) | 20
Profile | 3
Rating | 3 | LamTT |  | 20 | 20 | 15 | 10 | 6 | 2 | 0 | 0
Create Course | 3
Update UI create course | 3 | QuangNN |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Register Teacher | 4
Fix upload video | 4 | NguyenDH |  | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0
Request | 10
Request course notification | 5 | HieuLN |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Request session notification | 5 | HieuLN |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
TeacherProfile | 3
Loading intro clip | 3 | QuangNN |  | 10 | 10 | 6 | 4 | 2 | 0 | 0 | 0
Customize code | 5
Validate exception | 5 | HieuLN |  | 40 | 35 | 28 | 24 | 18 | 12 | 6 | 0
Total |  |  |  | 104 | 99 | 75 | 60 | 44 | 28 | 16 | 0

## Sprint 11
Sprint 11 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 11 (24/7 - 31/7) | 11
Document | 3
Test Plan | 3 | HieuLN | Complete | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Test Case | 2 | QuangNN | Complete | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0
Quality Assurance | 8
Quality Assurance for API | 4 | NguyenDH HieuLN | Complete | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 0
Quality Assurance for Mobile | 4 | LamTT HieuLN | Complete | 40 | 40 | 10 | 10 | 6 | 2 | 0 | 0
Total |  |  |  | 102 | 102 | 58 | 46 | 30 | 14 | 0 | 0

## Sprint 12
Sprint 12 Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Sprint 12 (31/7 - 7/8) | 3
Document | 3
Installation guide | 3 | NguyenDH HieuLN | Complete | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0
User guide | 2 | QuangNN LamTT | Complete | 15 | 15 | 10 | 5 | 0 | 0 | 0 | 0
Total |  |  |  | 25 | 25 | 15 | 5 | 0 | 0 | 0 | 0